## Legends Abbrivations
Abbreviation | Full Form | Description
PO | Product Owner | Responsible for overall scope ownership and stakeholder alignment
BA | Business Analyst | Responsible for requirement analysis and FSD preparation
BRD | Business Requirement Document | High-level business requirement document
FSD | Functional Specification Document | Detailed functional requirement document
CR | Change Request | Enhancement or modification to existing system
AGEL | All Projects (PO Level Tracking) | Central tracking board for all projects/CRs
CMF | Change Management Form | Document covering impact assessment & implementation plan
SIT | System Integration Testing | Internal testing phase before UAT
UAT | User Acceptance Testing | Client validation testing phase
QA | Quality Assurance | Testing team responsible for validation
SA | Solution Architect | Responsible for technical design validation
SOW | Statement of Work | Contractual scope document
Dev | Development | Technical implementation team

## Normal CR
Normal Project Change / CR
Sr. No. | Phases | Role/Responsibilities | Azure board | Owner | Attendees | Prerequisite
| AGEL - All Project | (PO Level Trcaking) | (Process Manager / Product Level Tracking)
1 | Create Epic | PO creates Client-Specific Epic in AGEL for new CR/project. | Epic created | Product Owner | Product Owner | Azure access
2 | Create Feature | PO creates Features under Epic based on approved BRD scope. | Feature + Subtasks created | Product Owner | Product Owner | Approved BRD
3 | BRD & Artifacts | PO prepares BRD, Artifacts, Project Plan, Phases, SOW and attaches to Azure Ticket. Client sign-off mandatory. | Documentation task tracked | Product Owner | Product Owner | BRD
4 | Project Kick-Off | Internal kickoff for scope review and alignment. | Meeting tracked | Product Owner | PO, BA Lead, Dev Lead, QA Lead, Solution Architect | Signed BRD
5 | FSD Preparation | BA Manager prepares FSD. PO tracks status. | FSD story created | BA Lead | BA Team | Approved BRD
6 | FSD Walkthrough | FSD walkthrough with stakeholders. | Walkthrough story created | BA Lead | PO, Dev Lead, QA Lead, Solution Architect | FSD
7 | Design | Technical design prepared by Dev Lead & Solution Architect. | Design story created | Dev Lead | Dev Lead, Solution Architect | FSD sign-off
8 | Development | Development activities executed as per approved design. | Development stories tracked | Dev Lead | Development Team | Approved Design
9 | Code Review | Code review conducted by Dev Lead & Solution Architect. | Review task created | Dev Lead | Dev Lead, Solution Architect | Development completed
10 | CMF Walkthrough | Change Management Form review including impact assessment and implementation plan validation. | CMF story created | Change Manager | PO, Dev Lead, QA Lead, Solution Architect | Implementation Plan, Impact Assessment, CMF
11 | SIT Code Migration | Deploy code to SIT environment. | Migration story created | Dev Lead | Dev Lead, QA Lead | Approved CMF
12 | SIT Testing | Execute SIT test cases and log defects. | SIT story created | QA Manager | QA Team | SIT Deployment
13 | UAT Code Migration | Deploy code to UAT environment. | Migration story created | Dev Lead | Dev Lead, QA Lead | SIT Sign-off
14 | UAT | Client UAT execution and validation. | UAT story created | QA Manager | QA Team, Client | UAT Deployment
15 | Finalization (Code Commit) | Final approval and branch merge validation. | Finalization task | Solution Architect | Solution Architect | UAT Sign-off
16 | Production Migration & Checklist Review | Production deployment with checklist validation. | Production migration story | Dev Lead | Product Owner, Dev Lead | Approved CMF + UAT Sign-off
17 | User Verification Test | Post-production validation for users/transactions. | Verification task created | Product Owner | Product Owner, QA Team, Client | Production Deployment
18 | Code Synchronization | Ensure code consistency across environments if applicable. | Sync task created | Dev Lead | Dev Lead | Production Stable
19 | Project Handover | Formal handover to Support/Maintenance Team. | Handover tracked | Change Manager | Product Owner, Client | Client Sign-off
20 | Project Closure | Formal closure of CR in tracking tools after approval. | Closure update | Change Manager | Change Manager | Client Approval

## Unscheduled
Unscheduled Change
Sr. | Phases | Owner | Attendees | Prerequisite
1 | Create Project | Project Manager | Project Manager | System Access
2 | BRD and Artifacts | Project Manager | Project Manager | BRD
3 | Project Kick Off | Project Manager | Project Manager, BA Lead, Technical Lead, QA Lead, Solution Architect | BRD
4 | FSD Document Preparation | Business Analyst Team | Business Analyst Team | Approved BRD
5 | FSD Walkthrough | Business Analyst Lead | Project Manager, BA Lead, Technical Lead, QA Lead, Solution Architect | FSD
6 | Design | Technical Lead | Technical Lead, Solution Architect | FSD Sign-off
7 | Source Checkout (If Applicable) | Technical Lead | Technical Lead, Solution Architect | Source Code Availability
8 | Development | Technical Lead | Development Team | Approved Design
9 | Code Review | Technical Lead | Technical Lead, Solution Architect | Development Completed
10 | Change Walkthrough | Change Manager | Change Manager, Project Manager, Technical Lead, QA Lead, Solution Architect | Implementation Plan, Impact Assessment, Change Document
11 | SIT Code Migration | Technical Lead | Technical Lead, QA Lead | Approved Change Document
12 | SIT Testing | QA Manager | QA Team | SIT Deployment
13 | UAT Code Migration | Technical Lead | Technical Lead, QA Lead | SIT Sign-off
14 | UAT | QA Manager | QA Team, Client | UAT Deployment
15 | Testing Sign-off | QA Manager | QA Team, Client | Test Completion & Client Confirmation
16 | Change Approval Board (CAB) | Change Manager | Change Manager, Project Manager, Technical Lead, QA Lead, Solution Architect | SIT, UAT Sign-off, Client Approval, Migration Plan
17 | Finalization | Solution Architect | Solution Architect | CAB Approval
18 | Production Migration | Deployment Team Lead | Project Manager, Technical Lead, Deployment Team | Approved Migration Plan
19 | User Verification Test | Deployment Team Lead | Project Manager, Deployment Team, Client | Production Deployment
20 | Code Synchronization (Primary to Secondary) | Deployment Team Lead | Project Manager, Deployment Team | Production Stabilized
21 | Project Closure Initiation | Change Manager | Project Manager, Change Manager, Client | Client Sign-off
22 | Project Closed | Change Manager | Change Manager | Formal Closure Approval

## Bug Fix
Bug Fix Change
Sr. No | Phase | Owner | Attendees | Prerequisite
1 | Create Project | Project Manager | Project Manager | System Access
2 | Design | Technical Lead | Technical Lead, Solution Architect | Approved Requirement
3 | Source Checkout (If Applicable) | Technical Lead | Technical Lead, Solution Architect | Source Code Availability
4 | Development | Technical Lead | Development Team | Approved Design
5 | Code Review | Technical Lead | Technical Lead, Solution Architect | Development Completed
6 | SIT Code Migration | Technical Lead | Technical Lead, QA Lead | Implementation Plan, Impact Assessment, Change Document
7 | SIT Testing | QA Manager | QA Team | SIT Deployment
8 | UAT Code Migration | Technical Lead | Technical Lead, QA Lead | SIT Sign-off
9 | UAT | QA Manager | QA Team, Client | UAT Deployment
10 | Test Sign-Off | QA Manager | QA Team, Client | Test Completion & Client Confirmation
11 | Finalization | Solution Architect | Solution Architect | Test Sign-Off
12 | Production Migration | Deployment Lead | Project Manager, Technical Lead, Deployment Team | Approved Migration Plan
13 | User Verification Test | Deployment Lead | Project Manager, Deployment Team, Client | Production Deployment
14 | Code Synchronization (Primary to Secondary) | Deployment Lead | Project Manager, Deployment Team, Client | Production Stabilized
15 | Project Closure Initiation | Change Manager | Project Manager, Change Manager, Client | Client Sign-Off
16 | Project Closed | Change Manager | Change Manager | Formal Closure Approval

## Emergency Change
Emergency Change
Sr. No | Phase | Owner | Attendees | Prerequisite
1 | Create Project | Project Manager | Project Manager | System Access
2 | BRD & Artifacts | Project Manager | Project Manager | Approved BRD
3 | Design | Technical Lead | Technical Lead, Solution Architect | FSD Sign-Off (Client & BA)
4 | Source Checkout (If Applicable) | Technical Lead | Technical Lead, Solution Architect | Source Code Availability
5 | Development | Technical Lead | Development Team | Approved Design
6 | Code Review | Technical Lead | Technical Lead, Solution Architect | Development Completed
7 | SIT Code Migration | Technical Lead | Technical Lead, QA Lead | Implementation Plan, Impact Assessment, Change Document
8 | SIT Testing | QA Manager | QA Team | SIT Deployment
9 | UAT Code Migration | Technical Lead | Technical Lead, QA Lead | SIT Sign-Off
10 | UAT | QA Manager | QA Team, Client | UAT Deployment
11 | Test Sign-Off | QA Manager | QA Team, Client | Test Completion & Client Confirmation
12 | Change Approval Board (CAB) | Change Manager | Project Manager, Technical Lead, QA Lead, Solution Architect | SIT & UAT Sign-Off, Client Approval, Migration Plan, Downtime Approval (if applicable)
13 | Finalization | Solution Architect | Solution Architect | CAB Approval
14 | Production Migration | Deployment Lead | Project Manager, Technical Lead, Deployment Team | Approved Migration Plan
15 | User Verification Test | Deployment Lead | Project Manager, Deployment Team, Client | Production Deployment
16 | Code Synchronization (Primary to Secondary) | Deployment Lead | Project Manager, Deployment Team, Client | Production Stabilized
17 | Project Closure Initiation | Change Manager | Project Manager, Change Manager, Client | Client Sign-Off
18 | Project Closed | Change Manager | Change Manager | Formal Closure Approval

## BAU
BAU - Business As Usual
| Phases | Owner | Attendees | Prerequisite
1 | Create Project | Project Manager | Project Manager | Access to Project Manager
2 | Production Migration | Project Manager | Project Manager
3 | User Verification Test | Project Manager | Project Manager, Client
4 | Code Synch from PR to DR | Project Manager | Project Manager, Client
5 | Project Closure | Assign to Change Manager | Change Manager, Client | Client sign off
6 | Project Closed | Assign to Change Manager | Change Manager | Change closed based on client sign off

## Other Actions
Escalation Matrix | To be defined
Client Communication | Basecamp
Review | Weekly team status review
Project Update | Weekly project status reporting